## Closure Checklist
ID | Closure Activity | Owner | Status | Evidence / Deliverable | Notes
CL-001 | Confirm BRD and FRD baseline | Business Analyst | Completed | BRD.pdf; FRD.pdf | Verify latest approved versions
CL-002 | Confirm requirements traceability | Business Analyst | Completed | RTM / User Stories Traceability | BRD → FRD → US → UAT
CL-003 | Review approved change requests | Business Analyst | Completed | Change_Request_Log.xlsx | Pending CR-005 remains visible
CL-004 | Confirm UAT coverage | Business Analyst / Business Owner | Ready for execution | UAT_Test_Cases.xlsx | Execution status should be updated only after testing
CL-005 | Confirm dashboard requirements | BI / Business Analyst | Completed | PowerBI_Dashboard_Specification.pdf | PBIX implementation is separate
CL-006 | Capture open risks and actions | Project Manager | Pending | Project risk/action log | Assign owners and due dates
CL-007 | Obtain stakeholder acceptance | Business Owner | Pending | Sign-off / acceptance record | Do not claim approval without evidence
CL-008 | Archive final project artifacts | Business Analyst | Pending | GitHub repository | Use clear version naming

## Recommendations
Priority | Recommendation | Benefit | Suggested KPI
P1 | Standardize KPI definitions | Reliable management reporting | KPI reconciliation variance
P1 | Publish executive dashboard | Faster decisions | Dashboard adoption / refresh success
P1 | Monitor returns by region/category | Identify operational issues | Return rate
P2 | Track new vs repeat customers | Retention insight | Repeat customer rate
P2 | Review product performance | Better sales planning | Revenue by product/category
P3 | Implement role-based access | Reporting governance | Access review completion