## UAT Test Cases
Test ID | User Story | Module | Test Scenario | Precondition | Test Steps | Expected Result | Priority | Status
UAT-001 | US-001 | Executive dashboard | Verify Total Revenue displays correctly | Valid completed-order data is loaded | Open dashboard | Total Revenue matches approved SQL/Excel calculation | High | Not Executed
UAT-002 | US-001 | Executive dashboard | Verify Completed Orders KPI | Valid data is loaded | Open dashboard | Completed Orders equals count of qualifying completed orders | High | Not Executed
UAT-003 | US-001 | Executive dashboard | Verify AOV calculation | Revenue and completed orders exist | Open dashboard | AOV = Total Revenue / Completed Orders | High | Not Executed
UAT-004 | US-002 | Date filter | Verify date slicer | Dashboard is open | Select a valid date range | All applicable KPIs and visuals update to selected period | High | Not Executed
UAT-005 | US-003 | Region filter | Verify regional filtering | Dashboard is open | Select South region | Regional KPI values reflect only selected region | High | Not Executed
UAT-006 | US-004 | Category analysis | Verify category revenue | Category data exists | Open category visual | Revenue is displayed by category and matches source calculation | Medium | Not Executed
UAT-007 | US-005 | Customer analysis | Verify New vs Repeat classification | Customer IDs are available | Open customer page | Customer classification follows approved business rule | High | Not Executed
UAT-008 | US-006 | Returns | Verify Return Rate | Return and qualifying order data exists | Open returns page | Return Rate matches approved formula | High | Not Executed
UAT-009 | US-007 | Finance validation | Reconcile KPI values | Approved KPI definitions available | Compare dashboard with SQL/Excel | Values match within approved tolerance | Critical | Not Executed
UAT-010 | US-008 | Refresh status | Verify refresh timestamp | Dashboard refreshed | View dashboard metadata | Latest refresh date/time is visible | Medium | Not Executed
UAT-011 | US-009 | Security | Verify authorized access | Test roles configured | Login using authorized role | User sees data permitted for role | Critical | Not Executed
UAT-012 | US-009 | Security | Verify restricted data | Restricted field exists | Login using unauthorized role | Restricted customer information is not exposed | Critical | Not Executed
UAT-013 | US-010 | Drill-down | Verify category-to-product drill-down | Dashboard contains hierarchy | Select a category and drill down | Product detail reflects selected category/filter context | Medium | Not Executed
UAT-014 | US-011 | Traceability | Verify requirement-to-test mapping | Approved requirement IDs exist | Review RTM | Each applicable requirement maps to one or more UAT cases | High | Not Executed
UAT-015 | US-012 | Change control | Verify impact assessment | Change request is raised | Review change request | Affected requirements, documents and tests are identified before approval | Medium | Not Executed

## RTM
Business Requirement | Functional Requirement | User Story | UAT Test ID | Status
BR-001 | FR-001 | US-001 | UAT-001 | Not Executed
BR-002 | FR-002 | US-002 | UAT-004 | Not Executed
BR-002 | FR-003 | US-003 | UAT-005 | Not Executed
BR-002 | FR-007 | US-004 | UAT-006 | Not Executed
BR-003 | FR-008 | US-005 | UAT-007 | Not Executed
BR-004 | FR-009 | US-006 | UAT-008 | Not Executed
BR-005 | FR-011 | US-007 | UAT-009 | Not Executed
- | FR-012 | US-008 | UAT-010 | Not Executed
BR-008 | FR-014 | US-009 | UAT-011 / UAT-012 | Not Executed
- | FR-010 | US-010 | UAT-013 | Not Executed
BR-009 | FR-015 | US-011 | UAT-014 | Not Executed
BR-010 | - | US-012 | UAT-015 | Not Executed

## UAT Summary
Metric | Value
Total Test Cases | 15
Critical Priority | 4
High Priority | 7
Medium Priority | 4
Passed | 0
Failed | 0
Blocked | 0
Not Executed | 15