## Change Request Log
Change ID | Date | Requested By | Change Request | Reason / Business Need | Impact Area | Priority | Impact | Effort | Affected Documents | Status | Approver | BA Action
CR-001 | 2023-01-18 | Head of Sales | Add product-level revenue and units sold to dashboard | Sales team needs product performance visibility | Reporting | High | Medium | Medium | FRD; Dashboard Requirements; User Stories; UAT | Approved | Business Owner | Impact analysis and requirement updates
CR-002 | 2023-02-03 | Finance Manager | Add completed-order revenue KPI excluding cancelled orders | Finance requires a reconciled revenue definition | KPI Definition | High | High | Medium | BRD; Business Rules; FRD; DAX; UAT | Approved | Finance Manager | Update KPI rule and acceptance criteria
CR-003 | 2023-02-15 | Operations Manager | Add return-rate analysis by region and category | Identify operational areas with elevated returns | Analytics | Medium | Medium | Low | FRD; Power BI Specification; UAT | Approved | Project Sponsor | Update dashboard scope and test cases
CR-004 | 2023-03-01 | Customer Experience Lead | Add new vs repeat customer segmentation | Support customer retention analysis | Customer Analytics | Medium | Medium | Medium | FRD; User Stories; DAX; UAT | Approved | Business Owner | Add rule, story and validation scenario
CR-005 | 2023-03-10 | Security / IT | Restrict dashboard access by business role | Limit sensitive reporting access to authorized users | Security | High | High | Medium | FRD; NFR; UAT | Pending | IT Owner | Assess security impact and prepare UAT case

## Impact Analysis
Change ID | Scope Impact | Requirement Impact | Data / Model Impact | Report Impact | UAT Impact | Risk | Recommendation
CR-001 | In scope | FR-006 / FR-007 | No structural change; add aggregations | Add product KPI visuals | Add product validation cases | Low | Approve
CR-002 | In scope | BR-002 / FR-001 | Revenue measure logic changes | Update KPI card and documentation | Reconcile with Finance sample | Medium | Approve with Finance sign-off
CR-003 | In scope | FR-009 | No source change | Add regional/category return visuals | Add filter and return-rate tests | Low | Approve
CR-004 | In scope | FR-010 | Customer classification logic | Add segmentation visual | Validate customer classification | Medium | Approve
CR-005 | Controlled scope | NFR / security requirement | Role mapping required | Apply row/report permissions | Security and access tests required | High | Approve only after security review

## Change Summary
Metric | Value
Total Change Requests | 5
Approved | 4
Pending | 1
High Priority | 3
High Impact | 3
BA Focus | Traceability, impact assessment, requirement updates, stakeholder communication and UAT alignment